## Slide 1
WEEKLY UPDATE · AUGUST 2026 · ABU DHABI
EXECUTIVE AGENT · AGENTICAD PHASE 1
Executive Agent
on SAP
A secure, auditable Microsoft-based agent that answers executive questions live from SAP — nine capabilities, delivered to a 30 September issuance date.
Design principle
—
No new access rights. Every answer is trimmed by the user's existing SAP authorisations and recorded on both sides — auditable end to end. This week's MCP server build carries that principle into the SAP integration layer itself.
فيلورا
Velora ▸
ELEVATING EVERY JOURNEY
Prepared for Velora · Abu Dhabi, United Arab Emirates

## Slide 2
PHASE 1 · CAPABILITY COVERAGE
The AI agent — nine capabilities
فيلورا
Velora ▸
ELEVATING EVERY JOURNEY
Covered
Partial
Next phase
5 covered · 2 partial · 2 next phase
01
ENTERPRISE DATA QUERY
COVERED
AR, AP, P&L, budget variance, Emiratisation, headcount — answered from SAP, trimmed to the executive's own permissions.
02
PROACTIVE RECOMMENDATION
COVERED
Covered on the six agreed KPIs. On an Emiratisation review it flags hiring/headcount and the change % unprompted.
03
EVALUATION ENGINE
COVERED
Evaluates against existing data — e.g. Emiratisation at 80% of the UAE standard, current vs target.
04
BRIEFING & SYNTHESIS
COVERED
Connected to the executive inbox for briefs, digests and synthesis ahead of meetings.
05
AGENT CREATION
NEXT PHASE
Deferred until data governance is in place, so agents are created within a governed scope.
06
INSTITUTIONAL MEMORY
COVERED
Meeting notes and documents searchable for executives and their successors from go-live.
07
MEETING INTELLIGENCE
PARTIAL
Minutes and action tracking covered. Completely covered with an external party (MDS) for live call-join and follow-up.
08
PEER BENCHMARKING
NEXT PHASE
Deferred until approved benchmark data is provided.
09
DECISION TRACEABILITY
PARTIAL
Copilot-side covered. Completely covered when Purview is provisioned — full dual audit.
Velora · AgenticAD Executive Agent · Phase 1 coverage
Confidential · August 2026

## Slide 3
ARCHITECTURE · DELEGATED IDENTITY
The Executive Agent — end to end
فيلورا
Velora ▸
ELEVATING EVERY JOURNEY
API / data call
Identity trust / delegation
Audit & telemetry
No new access — the query runs in SAP as the named executive, trimmed by the user's own PFCG/RBP authorisations, and recorded twice — SAP's Read-Access Log and Purview.
Velora · delegated identity · no service account on the interactive read path
Confidential · August 2026

## Slide 4
SAP ACTIVITIES · COVERED
Six executive queries, live from SAP
فيلورا
Velora ▸
ELEVATING EVERY JOURNEY
SAP-side services are active and ready. The executive asks in M365 Copilot; the agent queries S/4HANA and SuccessFactors under the executive's own SAP roles and returns a sourced, permission-trimmed answer.
01
Headcount
Headcount and position-count queries, trimmed by SuccessFactors role-based permissions.
SuccessFactors · EmpJob
02
Emiratisation
Emiratisation ratio served as an aggregate KPI only — the PDPL rule enforced by design, no personal records.
SuccessFactors OData
03
Receivables / Revenue
Receivables aging buckets — who owes what, how overdue — without raising a report request.
S/4HANA · FI Accounts Receivable
04
Payables
Open payables and their aging — upcoming payment exposure visible in one question.
S/4HANA · FI Accounts Payable
05
P&L
Live profit & loss view on demand — revenue, cost and margin by period, from the finance ledger.
S/4HANA · Finance
06
Budget Variance
Budget vs actual with the variance drivers, cited to source.
S/4HANA · Finance
Front door: M365 Copilot / Teams
Permission-trimmed at source — PFCG & RBP
Every answer: reasoning · sources · confidence → C9 audit log
Velora · C1 Enterprise Data Query · SAP services active
Confidential · August 2026

## Slide 5
WEEKLY STATUS
Where we are this week
فيلورا
Velora ▸
ELEVATING EVERY JOURNEY
Done this week
delivered
MCP server for SAP S/4HANA — built and confirmed working.
MCP server for SAP SuccessFactors — built and integrated with QA data; testing in progress.
Detailed working session held with the infra team.
Planned next week
this coming week
Restore SAP DEV/QA and complete unit testing on both MCP servers.
Deploy the MCP server(s) to Azure Container Apps.
Test SAP data routes via the intranet/private path, not the public internet.
Chase Cyber Security for a firm VM/container/Dataverse sign-off date.
HR to supply the Emiratisation data source; ADD to supply the audit format.
Issues & blockers
called out
SAP DEV/QA environment down since Mon 3 Aug — still down; blocking unit testing.
VM/container/Dataverse — infra complete, Cyber Security sign-off pending.
SF MCP server holds QA data only; PROD connection needs approval.
Emiratisation % not tracked by HR function today — must be supplied.
C9 audit storage/reporting format awaited from ADD.
We are in Sprint 1 · Spine & SAP. MCP-based SAP integration is built and testing; Sprint 0's environment/security items are still open and are now the pacing risk alongside the DEV/QA outage.
Velora · AgenticAD Executive Agent · weekly status
Confidential · August 2026

## Slide 6
SCHEDULE TRACKING · NEW THIS WEEK
Baseline vs. actual
فيلورا
Velora ▸
ELEVATING EVERY JOURNEY
Baseline anchor: 15 July 2026 (confirmed). Deviation is measured against the Sprint 0–5 schedule issued at kickoff.
M0 · Foundations gate
RED
Baseline: 24 Jul 2026
Open — Cyber Security sign-off pending on VM / container / Dataverse
Deviation: 10+ working days behind, still open
M1 · Sprint 1 exit
AMBER
Baseline: 7 Aug 2026 — closes today
MCP servers built; unit testing incomplete — SAP DEV/QA down since Mon 3 Aug
Deviation: At risk of slipping past today's baseline
Milestone | Baseline | This week's status | Deviation
M2 — Sprint 2 exit | 21 Aug 2026 | Not started | —
M3 — Development complete (code freeze) | 4 Sep 2026 | Not started | —
M4 — System test complete | 18 Sep 2026 | Not started | —
M5 — Executive UAT sign-off | 24 Sep 2026 | Not started | —
M6 — Deployed / issued | 29 Sep 2026 | Not started | —
ADAA deadline | 30 Sep 2026 | 5-day buffer intact — under pressure from M0/M1 slip | Watch
Velora · schedule baseline vs actual · interactive toggle in the HTML file
Confidential · August 2026

## Slide 7
PREREQUISITES · ARCHITECTURE & DEVELOPMENT VIEW
What we need, and by when
فيلورا
Velora ▸
ELEVATING EVERY JOURNEY
Blockers older than 5 working days escalate to the sponsor. Completed items shown in green.
Software licences
INFRA
by 20 Jul
✓ M365 Copilot — provided (3 dev/test + 1 CEO).
Power Platform premium + Dataverse — Dataverse is the ADAA audit database.
✓ Entra ID P1/P2 — already in place by default.
Developer access & workspace
CYBER SEC
escalated
Data Science VM, container app environment & Dataverse — infra build complete.
Now pending Cyber Security review and sign-off — this week's critical path.
Entra ID access — Client ID + Client secret for the on-behalf-of flow.
Purview access — audit-log read for the dual audit trail.
Azure & SAP readiness
SAP LEAD
in progress
✓ SAP-side enablement — OData for six queries, least-privilege user. Active & ready.
✓ SAP S/4 MCP server — built and working.
SAP SuccessFactors MCP server — built, QA data connected; PROD access needs approval.
Written confirmations · AgenticAD PMO
DAVID
by 15 Aug
Sub-agent rule — executive-created agents count as “without IT involvement”.
ADAA evidence format — how evidence is packaged; pack built per capability.
C9 audit storage & reporting format — requested from ADD, awaited.
Critical path: Cyber Security sign-off on VM/container/Dataverse, and the SAP DEV/QA outage, are the two items pacing this week's build.
Velora · prerequisites · owners & target dates
Confidential · August 2026

## Slide 8
DELIVERY BOARD · WHO IS DOING WHAT
Six sprints — all tasks, owners & status
فيلورا
Velora ▸
ELEVATING EVERY JOURNEY
Complete
In progress
Not started
Blocked
35 tasks across S0–S5 · full sprint & owner filters in the interactive HTML
FOUNDATIONS & ENVIRONMENTS · S0
6 · Cyber Sec pending
F1 · Delivery baseline, sprint plan & kickoff
PMO Lead
F2 · Licence position & capacity forecast
PMO Lead
F3 · Power Platform Dev/Test/Prod, DLP & ALM
Architect
F4 · Dataverse solution shell & logging schema
Maker B
F5 · Security baseline — Purview, conditional access
Security Lead
F6 · Developer workstation & named tenant identity
Architect
SAP READINESS · S0
5 · complete
P1 · Integration lead nominated; OData list drafted
SAP Lead
P2 · Least-privilege technical user created
SAP Lead
P3 · OData services activated for the six queries
SAP Lead
P4 · Network path confirmed — private endpoint
Architect
P5 · Representative demo dataset agreed (fallback)
Data Owner
AGENT BUILD · SPINE & SAP · S0–S1
8 · MCP layer live
A1 · Master Agent shell baselined (Copilot Studio)
PMO Lead
A2 · C9 Decision Traceability — reasoning, sources
Maker B
A3 · SAP S/4 MCP server built & working
Maker B
A4 · SAP SF MCP server — QA data; PROD pending
Maker B
A5 · C1 Enterprise Data Query — SAP OData connection
Maker B
A6 · C4 Briefing & Synthesis — Copilot native config
Maker A
A7 · Master Agent orchestration v1
Maker A
A8 · Leave handover — deputy brief
PMO Lead
AUTOMATION · S2
Not started
5 tasks
C2 recommendation engine, C7 flows, C5 logging, C1 hardening — Maker B
INSTRUCTION LAYER · S3
Not started
5 tasks
C3 Evaluation, C6 Institutional Memory, C5 journey, C8 Benchmarking — Maker A
SYSTEM TEST · S4
Not started
1 task
Capability scripts, regression, security & injection probes — Security Lead
UAT & DEPLOY · S5
Not started
5 tasks
Executive UAT, production deploy, Adoption Index, hypercare, evidence pack
Velora · delivery board · owners & status · full interactive board in the HTML file
Confidential · August 2026

## Slide 9
RAID
Risks & issues under management
فيلورا
Velora ▸
ELEVATING EVERY JOURNEY
REF
RISK / ISSUE
RAG
MITIGATION & POSITION
R8
Prerequisites outstanding beyond the escalation threshold
Red
Infra-side build (VM/container/Dataverse) complete. Now blocked on Cyber Security review — recommend a named owner and date.
R12
SAP DEV/QA environment down, blocking unit testing
Red
Down since Mon 3 Aug. Needed to complete MCP server unit testing for C1/C9.
R2
SAP OData exposure / technical user delayed by hypercare
Green
Resolved — SAP OData for the six queries, plus SAC, active. MCP servers now built on top.
R9
Emiratisation % not maintained in SAP SuccessFactors
Amber
Not currently tracked by the HR function. HR to supply source and refresh cadence before C1/C3 can serve it as SAP-governed.
R10
C9 audit trail storage & reporting design open
Amber
Format to be provided by ADD — requested, not yet received. Target design already specified in the Architect Brief.
R11
SF MCP server connected to QA data only
Amber
PROD data connection requires approval before this capability can move beyond testing.
R1
Stricter reading of the sub-agent requirement
Amber
Written confirmation requested and chased weekly. Fallback design already scoped.
R3
August leave thins build capacity in the critical window
Amber
Sprint 1 sequenced before leave; Sprint 2 developer-only; Deputy carries the delivery tier.
R5
Adoption reporting template arrives late
Amber
Broad telemetry instrumented now so most index formulas are computable retrospectively.
R7
Prompt injection or data exfiltration via connected paths
Amber
Least privilege, permission trimming, DLP; MCP endpoints now live — Sprint 4 test scope to include container isolation & transport security checks.
R4
Credit burn on the daily autonomous scan exceeds forecast
Green
Forecast prepared; scan scope and frequency tunable. Checkpoint mid Sprint 2.
R6
Validation format unknown — demo, document or site visit
Green
Evidence pack built per capability from Sprint 1 so any format can be served.
Velora · RAID · R8/R12 red · R2/R4/R6 green · remainder amber
Confidential · August 2026