## Slide 1
FOLLOW-UP 1 OF 3
Nine-capability coverage: current, future and vendors
Management view as of the 30 September 2026 milestone (date to confirm)
Capability | Velora by 30 Sep | Velora beyond Sep | Protiviti claim | MeshX scope
C1 Enterprise data query | Covered — 6 SAP queries live | Expand via SAP BDC/BTP + Foundry | Full — SAP + SharePoint/OneLake | Foundation MCP; 3–5 questions
C2 Recommendations | Covered — daily KPI scan | Broader signals and skills | Full — Foundry scheduled skill | Not covered
C3 Evaluation engine | In progress — close and evidence | Deeper criteria/data models | Full — Foundry evaluation skill | Not covered
C4 Briefing & synthesis | Covered — inbox briefs/digests | More sources and automation | Full — cited Outlook/Teams briefs | Not covered
C5 Agent creation | Gated — governance + lifecycle | Full governed self-service | Full — create/edit/pause/retire | Not covered
C6 Institutional memory | Covered — documents/transcripts | Broader corpus and retention | Full — AI Search/RAG | Not covered
C7 Meeting intelligence | Covered — Graph + action flows | Broader channels/automation | Full — Graph/manual upload | Not covered
C8 Peer benchmarking | Planned — one approved source | Multi-source benchmarking | Full — one-source minimum | Not covered
C9 Decision traceability | Partial — Dataverse live; export/Purview | Dual audit + full governance | Full — Dataverse + CSV evidence | Data lineage/audit portion only
VELORA: 5 COMPLETE • 2 ACTIVE/PARTIAL • 2 GATED/PLANNED
PROTIVITI: 9 CLAIMED — NOT YET DELIVERED
MESHX: C1 + DATA-LAYER C9 ONLY
Key point: Protiviti is broader; MeshX is deeper only in governed data/lineage. Velora can reach capability parity without rebuilding the current SAP path.

## Slide 2
FOLLOW-UP 2 OF 3
What Velora must complete to cover Protiviti’s claims
Internal ownership is available; the remaining need is protected capacity, evidence and management decisions
Close the four remaining capability items
C3 — complete structured evaluation and evidence.
C5 — confirm “without IT” governance; prove create/edit/pause/retire.
C8 — demonstrate benchmarking against one approved source.
C9 — complete evidence schema and CSV export; use Dataverse if Purview is delayed.
Retest the five capabilities already covered
C1 — six permission-trimmed SAP queries.
C2 — scheduled KPI recommendations.
C4 — executive briefing and synthesis.
C6 — searchable documents/transcripts.
C7 — meeting intelligence and action flows.
Output: signed tests, screenshots, logs and business acceptance.
Add Protiviti-equivalent delivery controls
Requirements traceability matrix • formal SIT/integration/security/negative-path tests • UAT scripts and CEO/proxy booking • capability-level ADAA evidence • controlled release/rollback • runbooks, monitoring and full internal hypercare.
ACCOUNTABILITY
Owner | Role | Accountability
Bala | Developer Architect + Project Manager | Architecture, traceability, delivery plan, RAID/defects, documentation and coordination
Abdullah + Infrastructure team | Infrastructure and access | Non-Prod/Prod support, connectivity, environments, production readiness and access
SAP leads | Lakshmi • Abdelaziz • Kamalesh • Xavier • Rajesh • Kamal | System, integration, permission, security and negative-path testing
David • Shiva • Lakshmi | Business/UAT | UAT scripts, CEO/proxy sessions, expected results and business sign-off
Abdelaziz + Bala | Evidence and operations | ADAA evidence pack, runbooks, monitoring, incident ownership and escalation
Management position: Phase 1 can be covered internally. Additional resources do not replace the owners above—they create the capacity to fast-track C3/C5/C8/C9 and complete testing/evidence without weakening go-live support.

## Slide 3
FOLLOW-UP 3 OF 3
Delivery path: September completion and beyond-timeline scale
Keep Phase 1 stable; introduce SAP BDC, Azure AI Foundry/Azure Foundry and SAP DevOps as a governed next phase
DELIVERY TIMELINE
NOW–28 AUG
Close C3/C5/C8/C9
Freeze Phase 1 scope
SEP
SIT • security • UAT
release and evidence
30 SEP
Executive issuance /
production go-live
31 OCT
30-day recommendation +
evaluation logs complete
Phase 1 software and access
M365 Copilot + Teams
Copilot Studio
SAP BTP and SAP-direct MCP
S/4HANA • SuccessFactors • SAC endpoints
Entra delegated identity
Dataverse audit/evidence store
Graph transcript permissions
Non-Prod/Prod access and Infrastructure support
Purview access or approved Dataverse fallback
Beyond September architecture
SAP BDC — governed SAP data products, semantics, KPIs and lineage.
Azure AI Foundry / Azure Foundry — advanced recommendations, evaluations, benchmarking and reusable skills.
SAP BTP + standard MCP — controlled integration layer.
Dataverse + Purview — traceability and governance.
MeshX Foundation or Fabric/OneLake only where management approves a clear, non-duplicative role.
SAP DevOps and fast-track resources
Phase 1: controlled SAP transports, named approvals, version records and rollback—formal SAP DevOps pipeline does not yet exist.
Next phase: source control, automated testing, release gates, repeatable promotion and monitoring.
Fast-track ask: +1 Copilot/agent developer, +1 QA/UAT/evidence specialist and +1 SAP BDC/Foundry integration engineer.
DECISION REQUIRED
Protect the existing internal owners through go-live and approve a small surge team to fast-track the remaining capabilities. Treat SAP BDC + Azure AI Foundry/Azure Foundry + SAP DevOps as a separately governed next-phase roadmap—not a September re-platforming exercise.