## Slide 1
VELORA | EXECUTIVE AI AGENT
CONFIDENTIAL • 26 AUGUST 2026
REMAINING STEPS
What Velora must complete to cover Protiviti’s deliverables
Internal delivery is achievable; focus the remaining effort on four capability gaps, formal assurance and protected go-live capacity.
1 Close and evidence the capability gaps
C3 Evaluation —
complete structured evaluation, criteria, sources and logged evidence.
C5 Agent creation —
confirm “without IT” governance; prove create/edit/pause/retire and lifecycle logging.
C8 Benchmarking —
demonstrate one approved peer source with citations and method.
C9 Traceability —
complete evidence schema and CSV export; use Dataverse if Purview is delayed.
C1/C2/C4/C6/C7 —
retest existing functions and capture signed acceptance evidence.
2 Complete Protiviti-equivalent delivery controls
Traceability —
map every SOR requirement to component, owner, test and evidence.
Assurance —
formal system, integration, permission, security and negative-path testing.
UAT —
scripts, expected answers, CEO/proxy sessions and business sign-off.
Evidence —
capability-level ADAA pack plus recommendation/evaluation logs through 31 Oct.
Operations —
controlled release/rollback, runbooks, monitoring, incident escalation and full internal hypercare.
3 Secure platform, access and delivery capacity
Infrastructure —
Non-Prod/Prod support, SAP endpoints/private connectivity and production approval.
Access —
Entra delegated identity, Graph scopes, Dataverse and Purview or approved fallback.
SAP release —
controlled transports and rollback for Phase 1; formal SAP DevOps is a next-phase improvement.
Beyond September —
SAP BDC + Azure AI Foundry/Azure Foundry roadmap; MeshX/Fabric only with a clear non-duplicative role.
Fast-track capacity —
add 1 agent developer, 1 QA/UAT/evidence specialist and 1 SAP BDC/Foundry integration engineer.
ACCOUNTABILITY
Bala | Abdullah + Infrastructure | SAP leads | David • Shiva • Lakshmi | Abdelaziz + Bala
Architect + PM: traceability, architecture, RAID, documentation and coordination | Environments, access, connectivity and production readiness | Lakshmi • Abdelaziz • Kamalesh • Xavier • Rajesh • Kamal: formal testing | UAT scripts, CEO/proxy sessions and business sign-off | ADAA evidence, runbooks, monitoring and operational escalation
MANAGEMENT DECISION
Protect the named internal owners through go-live and approve the three-person surge capacity. This enables Velora to cover the Protiviti deliverables internally without re-platforming Phase 1.
Source: Velora SOR v1.0; internal weekly update 21 Aug 2026; Protiviti proposal; internal ownership confirmation
1